## Sheet1
id | title | phase | status | priority | owner | start_date | due_date | progress | objective | notes | color
1 | Biomedical Research Search Integration | Execution | Not Started | High | Science Team | 2024-10-01 | 2024-11-15 | 0 | Implement PubMed API integration with peer-review validation |  | None
2 | Employment Opportunity Matcher | Execution | Not Started | High | Commerce Team | 2024-10-01 | 2024-11-15 | 0 | Create semantic skill matching algorithm |  | Yellow
3 | Artisan Marketplace Connector | Execution | Not Started | High | Commerce Team | 2024-10-01 | 2024-11-15 | 0 | Build MVP connector for creative marketplaces |  | None
4 | Privacy Filters Implementation | Execution | Not Started | High | Security Team | 2024-10-01 | 2024-11-15 | 0 | Deploy PII redaction and anonymization |  | None
5 | Database Persistence Layer | Execution | Not Started | Medium | Infrastructure Team | 2024-10-01 | 2024-11-15 | 0 | Set up PostgreSQL with data models |  | None
6 | Provenance Enforcement Middleware | Stabilisation | Completed | High | Security Team | 2024-09-01 | 2024-09-30 | 100 | Implement mandatory source validation |  | Green
7 | Human-in-the-Loop Feedback System | Stabilisation | Completed | High | Product Team | 2024-09-01 | 2024-09-30 | 100 | Create feedback capture pipeline |  | Green
8 | Agent Safety Layer | Stabilisation | Completed | High | Security Team | 2024-09-01 | 2024-09-30 | 100 | Implement dry‑run and kill‑switch controls |  | Green
9 | Cross-Domain Knowledge Fusion | Discovery | Not Started | High | AI Team | 2024-11-01 | 2024-12-15 | 0 | Build unified ontology and fusion layer |  | None
10 | Cost Metering & Quotas | Discovery | Not Started | Medium | Infrastructure Team | 2024-11-01 | 2024-12-15 | 0 | Implement resource tracking and limits |  | None
11 | UBI Simulation Engine | Discovery | Not Started | Medium | Commerce Team | 2024-11-01 | 2024-12-15 | 0 | Create economic modeling framework |  | Yellow
12 | Creative Intelligence Tools | Discovery | Not Started | Medium | Arts Team | 2024-11-01 | 2024-12-15 | 0 | Develop attribution and originality scoring |  | None
13 | Load Testing Suite | Measurement | Not Started | Medium | QA Team | 2024-12-01 | 2025-01-15 | 0 | Implement comprehensive performance testing |  | None
14 | Security Penetration Testing | Measurement | Not Started | High | Security Team | 2024-12-01 | 2025-01-15 | 0 | Conduct thorough security audit |  | None
15 | Compliance Audit Framework | Measurement | Not Started | High | Legal Team | 2024-12-01 | 2025-01-15 | 0 | Build HIPAA/GDPR compliance verification |  | None
16 | Deployment Automation | Measurement | Not Started | Medium | DevOps Team | 2024-12-01 | 2025-01-15 | 0 | Create CI/CD pipeline and auto‑deployment |  | None